## Phases
Phase | Slug | Title | Key Deliverables | Key Code Touchpoints | DB / Schema | Config / Infra | GUI Proof (how to prove) | Exit Criteria | Status | Owner | Target Date
0 | indexlab-harness | IndexLab harness + live event stream baseline | IndexLab CLI + live event stream + IndexLab GUI tab | src/cli/run-one.js or new src/cli/indexlab.js; src/api/guiServer.js | None (artifacts only) | Optional: start docker/observability later | IndexLab tab shows live stage timeline + active jobs table + counters | Run 1 product; GUI updates live; events persisted
1 | needset-engine | Field state snapshot + NeedSet engine (tier + confidence aware) | NeedSetEngine + needset.json + NeedSet GUI panel | src/pipeline/runProduct.js; src/scoring/consensusEngine.js; src/validator/qualityGate.js | needset table (Phase 6 schema) optional; artifacts/needset.json | None | NeedSet table with need_score + reason badges; NeedSet size sparkline | NeedSet prioritizes deep high-stakes fields; shrinks after resolution
2 | searchprofile-aliases | Deterministic aliases + optional Flash‑Lite SearchProfile JSON | Deterministic alias builder + optional Flash-Lite SearchProfile JSON + GUI view | src/discovery/searchDiscovery.js; src/search/queryBuilder.js; src/research/queryPlanner.js | search_profiles table (Phase 6 schema) optional | LLM config keys | Search Profile card shows aliases + queries BEFORE search runs | Profile validated (digit groups preserved) and persisted
3 | provider-search-triage | Provider search + SERP logging + tier/doc_kind tagging + triage (Google/SearXNG) | Provider search logging + SERP Explorer + triage + searxng settings/docker | src/search/searchProviders.js; src/discovery/searchDiscovery.js; src/search/serpDedupe.js | search_queries + url_candidates tables | searxng/settings.yml + docker-compose (optional) | SERP Explorer shows candidates, tier/doc_kind, triage reasons | Audit trail for queries/results and top-K selection
4 | url-health-self-healing | 404/410/403/429 control loop + repair search + bad_url_patterns | url_health + repair search + bad_url_patterns + GUI health panels | src/research/frontierDb.js; fetch pipeline integration | url_health + bad_url_patterns | None | URL Health table shows cooldowns; repair queries fired; repeat 404 list | Repeat 404s stop; repair search produces replacements
5 | parallel-fetch-parse | Parallel fetch/parse (HTTP-first + browser escalation) + per-host backoff | Worker pools + parallel fetch/parse + HTTP-first + browser escalation + GUI worker panel | fetcher/*; src/pipeline/runProduct.js scheduler | fetches table extensions | None | Workers panel; HTTP vs browser mix; requests/min; stage waterfall | Time-to-first-indexed-doc drops; browser only used when needed
6 | evidence-index-db | EvidenceIndexDb (SQLite): docs + chunks + facts + FTS + stable snippet_id | EvidenceIndexDb SQLite + schema_v1.sql + chunks/facts/FTS + index explorer GUI | new src/index/evidenceIndexDb.js; adapters/tableParsing | schema_v1.sql (docs/chunks/facts/FTS, etc.) | SQLite WAL mode; batched writes | Indexed docs inventory + searchable index box | Re-run dedupe hits; FTS queries return snippets
7 | tier-retrieval-prime-sources | Tier-aware internal retrieval + Prime Sources builder | Tier-aware retriever + Prime Sources builder + GUI per-field evidence view | new src/retrieve/*; integration into pipeline | prime_sources + evidence_refs | None | Field drilldown: retrieval hits + prime sources + min_refs status | Prime sources satisfy evidence policy for high-stakes fields
8 | extraction-context-wiring | Extraction Context Matrix wiring into prompts + extraction dashboard | Extraction Context wiring + prompt contract + extraction dashboard | src/llm/extractCandidatesLLM.js; src/llm/fieldBatching.js | store evidence_refs and violations (optional) | Prometheus metrics + alerts (optional) | Extraction tab: batches, schema fail rate, dangling refs, min_refs satisfied | No accepted values without required evidence refs; failures visible
9 | convergence-loop-stop | Tier/confidence convergence loop + stop conditions (no key/alias infinite loops) | Explicit rounds + stop conditions + convergence dashboard | src/pipeline/runProduct.js orchestrator | run_events + needset history | None | Round summaries, escalation reason, stop reason, NeedSet trend | No infinite loops; external search only for remaining NeedSet
10 | learning-compounding | Safe learning/compounding (lexicon/anchors/url_memory/domain_yield) gated by acceptance | LearningUpdater + lexicon/anchors/url_memory/domain_yield + GUI feed | new src/learn/*; integration after acceptance | component_lexicon + field_anchors + url_memory + domain_field_yield | None | Learning feed shows changes with provenance; next run faster | Subsequent runs show fewer searches and improved Tier-1 hits
11 | workers-control | LAST: worker pool sizing controls + GUI knobs | LAST: configurable worker counts + GUI controls + safe backoff | src/config.js; scheduler from Phase 5; guiServer | store config snapshot in runs.config_json | None | Workers tab controls; throughput changes without 429 spike | Worker count tuning works predictably

## Bundle Files
Path | Type | Purpose / Notes
PHASE-00-indexlab-harness.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-01-needset-engine.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-02-searchprofile-aliases.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-03-provider-search-triage.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-04-url-health-self-healing.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-05-parallel-fetch-parse.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-06-evidence-index-db.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-07-tier-retrieval-prime-sources.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-08-extraction-context-wiring.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-09-convergence-loop-stop.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-10-learning-compounding.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
PHASE-11-workers-control.md | md | Phase prompt/spec: objectives, tasks, code touchpoints, GUI proof
README.md | md | Misc documentation
docker/docker-compose.observability.yml | yml | Docker compose for observability + optional SearXNG
docker/tempo.yaml | yaml | Docker compose for observability + optional SearXNG
grafana/dashboards/extraction-tab.json | json | Starter Grafana dashboards (import into Grafana)
grafana/dashboards/indexlab-overview.json | json | Starter Grafana dashboards (import into Grafana)
grafana/dashboards/sources-checklist.json | json | Starter Grafana dashboards (import into Grafana)
prometheus/alerts.indexlab.yml | yml | Prometheus scrape config and alert rules
prometheus/prometheus.yml | yml | Prometheus scrape config and alert rules
searxng/settings.yml | yml | SearXNG config for local/meta search
sql/schema_v1.sql | sql | SQLite DDL for EvidenceIndexDb + supporting tables