## Checklist
Spec Factory Phase Checklist (Repo: CdubVentures/spec-harvester)
Generated | Updated: 2026-02-13T07:32:17Z
Phase Summary
Phase | Phase name | Done | Partial | Not started | Unknown | Total | % Done
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | 20 | 0 | 0 | 0 | 20 | 100%
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | 13 | 0 | 0 | 0 | 13 | 100%
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | 12 | 0 | 0 | 0 | 12 | 100%
04 | MULTI-ROUND WEB CRAWLING & EVIDENCE COLLECTION PIPELINE | 6 | 0 | 0 | 0 | 6 | 100%
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | 11 | 0 | 0 | 0 | 11 | 100%
06 | IDENTITY GATE & PRODUCT DISAMBIGUATION SYSTEM | 4 | 0 | 0 | 0 | 4 | 100%
07 | PIPELINE ORCHESTRATOR, QUEUE MANAGEMENT & 24/7 DAEMON | 6 | 0 | 0 | 0 | 6 | 100%
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | 9 | 0 | 0 | 0 | 9 | 100%
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | 11 | 0 | 0 | 0 | 11 | 100%
10 | MULTI-CATEGORY EXPANSION, INTEGRATION TESTING & PRODUCTION HARDENING | 3 | 0 | 0 | 0 | 3 | 100%
11 | ADDENDUM: PRACTICAL CHATMOCK INTEGRATION ON WINDOWS (MODEL TIERING + AUTORECOVERY) | 5 | 0 | 0 | 0 | 5 | 1
ALL | All phases | 100 | 0 | 0 | 0 | 100 | 100%
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Authoring workbook + workbook_map present for category | Done | helper_files/mouse/mouseData.xlsm + helper_files/mouse/_control_plane/workbook_map.json | Keep map in sync with new fields; expand range beyond B9:B83 | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Generated field_rules.json exists | Done | helper_files/mouse/_generated/field_rules.json |  | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Generated ui_field_catalog.json exists | Done | helper_files/mouse/_generated/ui_field_catalog.json |  | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Generated known_values.json exists | Done | helper_files/mouse/_generated/known_values.json |  | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Generated component_db JSONs exist | Done | helper_files/mouse/_generated/component_db/*.json | Expand component types and ensure enums/components are normalized | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Generated key_migrations.json exists | Done | helper_files/mouse/_generated/key_migrations.json | Add migrations whenever keys are renamed; keep backward-compat tests | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Compilation report emitted (hashes/counts/diffs) | Done | helper_files/mouse/_generated/_compile_report.json | Use counts to enforce full-field coverage targets | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Field Rules Studio / control-plane editing UI exists | Done | tools/gui/app.py Field Rules Studio > Compile & Reports (Phase 1 gate metrics, guardrail checks, validate-rules trigger) | Preserve existing UI layout style; expand guardrail checks as new artifacts are added. | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | All intended mouse fields authored for current scope (75 keys, B9:B83) | Done | helper_files/mouse/_generated/_compile_report.json (field_count=75) + helper_files/mouse/_control_plane/workbook_map.json (key_list B9:B83) | When scope expands, extend workbook key range and regenerate artifacts. | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Critical + identity buckets populated (non-zero) | Done | helper_files/mouse/_generated/_compile_report.json counts: identity=1 critical=1; parse_templates coverage for required/critical/identity = 100% | Maintain expectations-driven priority enforcement and keep identity defaults for canonical identity keys. | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | parse_templates.json generated as standalone artifact | Done | helper_files/mouse/_generated/parse_templates.json + src/field-rules/compiler.js | Expand template coverage for all critical/required fields with richer context and negatives | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | cross_validation_rules.json generated as standalone artifact | Done | helper_files/mouse/_generated/cross_validation_rules.json + src/field-rules/compiler.js | Increase authored rule depth and category-specific consistency constraints | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | JSON Schema validation for generated artifacts (AJV) | Done | src/field-rules/compiler.js validateRules() + categories/_shared/*.json + AJV | Tighten schemas toward full strict contract and add CI gate in Phase 2 | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Compilation CLI command exists (category-compile) | Done | src/cli/spec.js | Add --dry-run / --diff / --watch options per plan | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Field rules verification command exists (field-rules-verify) | Done | src/cli/spec.js + src/ingest/fieldRulesVerify.js | Extend verification to ui_field_catalog/known_values/component_db consistency | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Watch mode for rule compilation (chokidar) | Done | src/field-rules/compiler.js watchCompileRules() + src/cli/spec.js compile-rules --watch | Watch mode supports debounce, max-events guardrails, and cross-platform chokidar behavior. | Medium
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Golden fixture for field_rules compile output | Done | src/ingest/fieldRulesVerify.js semantic/byte verification + src/cli/spec.js field-rules-verify --strict-bytes + test/fieldRulesVerify.test.js | Semantic compare now ignores volatile keys while retaining optional strict byte mode for CI parity checks. | Medium
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Golden benchmark harness for end-to-end outputs | Done | src/benchmark/goldenBenchmark.js + src/testing/goldenFiles.js + src/cli/spec.js benchmark/benchmark-golden + accuracy-report | Benchmark + accuracy reporting now available with per-field metrics and markdown export. | Medium
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Schema versioning & migrations (semver + key migrations) | Done | src/field-rules/migrations.js + src/field-rules/compiler.js key_migrations doc emission/validation + categories/_shared/key_migrations_schema.json + test/migrations.test.js | Semver classification + migration transforms now emit/validate structured migration docs; extend authoring UX for advanced merge/split curation later. | Medium
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Type generation (TS/Zod) from field rules | Done | src/build/generate-types.js + src/cli/spec.js generate-types + test/generateTypes.test.js | Generated Zod schemas + TS types from field_rules and known_values are now emitted deterministically. | Low
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | validate-rules CLI (schema + referential integrity) | Done | src/cli/spec.js validate-rules + src/field-rules/compiler.js | Add referential-integrity checks for enum/component links and migration safety | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Dry-run diff output (what changed + impact) | Done | src/cli/spec.js compile-rules --dry-run + compile-report + rules-diff + src/field-rules/compiler.js classification | Dry-run diff now paired with breaking/potentially-breaking classification via rules-diff output. | Low
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Single canonical FieldRulesEngine module exists and used by CLI+daemon+GUI | Done | Runtime engine is now enforced in runProduct, publish-time finalExporter, and override finalization workflow (no-bypass runtime gate across CLI/daemon/review paths). | Keep this as mandatory architecture invariant for future entrypoints. | High
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Evidence Auditor hard gate (value != unk requires url+snippet_id+quote) | Done | FieldRulesEngine.auditEvidence() now supports strict evidence invariants (source_id, snippet_hash, quote_span, retrieved_at, extraction_method) in addition to url/snippet_id/quote checks. | Wire strict-evidence enforcement across all publish paths once deterministic provenance is complete in crawler/extractors. | High
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | normalizeCandidate() driven by field_rules templates, units, shapes | Done | FieldRulesEngine.normalizeCandidate() now handles scalar/list coercion, unit conversion, ranges, url validation, and component_ref resolution (exact/alias/fuzzy via component DB). | Expand normalization-function library and add broader golden fixture coverage for less common data formats. | High
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Enum policy enforcement (closed/open + needs_curation) | Done | Closed/open enum policy enforced with alias resolution plus runtime curation queue signaling and persisted suggestions in helper_files/<category>/_suggestions/enums.json. | Continue expanding per-category known_values and curation review workflow. | High
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Cross-validation engine for field-level constraints | Done | FieldRulesEngine.crossValidate() now supports range, conditional_require, component_db_lookup, group_completeness, and mutual_exclusion checks. | Increase authored cross-validation rule depth per category and add replay-level regression coverage. | Medium
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Unknown builder produces standardized unknown objects (reason-coded) | Done | Unknown-object flow is now consistently reason-coded through engine normalization/evidence/cross-validation failures and override runtime demotion path. | Maintain unknown_reason taxonomy consistency in future pipeline modules. | High
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | applyKeyMigrations(record) used at publish time | Done | Publish path now applies key migrations through runtime engine before final write (writeFinalOutputs runtime gate + migration pass). | Keep key_migrations docs complete whenever fields are renamed/split/merged. | Medium
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Determinism tests: replay yields identical outputs across runs | Done | Determinism coverage added for repeated normalizeFullRecord runs and expanded runtime-gate/final-export regression tests. | Extend to larger replay fixture batches as Phase 10 hardening grows. | Medium
04 | MULTI-ROUND WEB CRAWLING & EVIDENCE COLLECTION PIPELINE | EvidencePack builder exists (snippets + references) | Done | EvidencePack v2 now emits source-level metadata, snippet hashes, normalized text, json_ld_product snippets, and strict provenance primitives. | Propagate deterministic extractor snippets into the same citation format for full strict-evidence parity. | High
04 | MULTI-ROUND WEB CRAWLING & EVIDENCE COLLECTION PIPELINE | Every accepted value is tied to EvidencePack snippet_id(s) + quote(s) | Done | Deterministic candidates now receive parser-native EvidencePack bindings (candidate_fingerprint -> snippet_id) and flow into provenance via evidenceRefs. | Maintain binding stability as extractor keyPath logic evolves and keep regression tests on fingerprint format. | High
04 | MULTI-ROUND WEB CRAWLING & EVIDENCE COLLECTION PIPELINE | Tiered source policy & domain approvals applied in crawling | Done | Tier/domain policy now loads from rich source registry metadata via category loader + planner sourceHostMap. | Continue tuning per-source field-coverage heuristics and tier-specific stop rules. | Medium
04 | MULTI-ROUND WEB CRAWLING & EVIDENCE COLLECTION PIPELINE | Caching, rate limits, and replayable fetch artifacts | Done | Replay artifacts remain in place; per-host and per-source rate limits are enforced in fetchers. | Add replay mode assertions in end-to-end crawl tests for no-network guarantees. | Medium
04 | MULTI-ROUND WEB CRAWLING & EVIDENCE COLLECTION PIPELINE | Source registry defined for mouse with >=5 tiered sources and per-source crawl config | Done | helper_files/mouse/sources.json + loader flattening of rich source metadata into sourceHostMap. | Expand health tracking fields and automated source freshness checks. | High
04 | MULTI-ROUND WEB CRAWLING & EVIDENCE COLLECTION PIPELINE | robots.txt compliance + per-source crawl delay enforced in fetch layer | Done | src/fetcher/robotsPolicy.js + PlaywrightFetcher/HttpFetcher robots checks and rate_limit_ms support. | Add deny/allow telemetry rollups to source health dashboards. | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | LLM extraction module exists | Done | src/llm/extractCandidatesLLM.js | Wire field_rules slice + enums/components into prompts | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | LLM validator module exists | Done | src/llm/validateCandidatesLLM.js | Make validator contract-driven and evidence-audited | Medium
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Prompts include field_rules + enum lists + component options | Done | extractCandidatesLLM now injects per-batch field contracts, enum options, and component DB refs into payload. | Keep prompt contracts aligned with field_rules schema evolution. | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Extractor outputs snippet_id + quote per candidate (not just evidenceRefs) | Done | LLM candidates now carry snippetId/snippetHash/quote/quoteSpan and pass evidence verifier before acceptance. | Enable strict verifier mode once all sources emit complete snippet metadata. | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | JSON-only enforcement + strict schema validation on LLM outputs | Done | callOpenAI enforces structured JSON schema with retry fallback; extraction schema expanded for citation fields. | Add additional schema-level constraints per field type as contracts harden. | Medium
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Deterministic parser module implemented (regex/spec-table/json-ld with citations) | Done | src/extract/deterministicParser.js + test/deterministicParser.test.js | Expand parser template coverage and context-negative matching per category. | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Component DB cross-reference auto-fill integrated in extraction flow | Done | src/extract/componentResolver.js + runProduct integration + test/componentResolver.test.js | Tune property-to-field mappings and add category-specific component enrichers. | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Field batching + model routing implemented with <=7 extraction calls per product | Done | src/llm/fieldBatching.js + extractCandidatesLLM batching tests | Tune per-batch evidence windows and routing thresholds from production telemetry. | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Content-addressed LLM extraction cache with TTL added | Done | src/llm/llmCache.js + cache integration in extractCandidatesLLM + test/llmCache.test.js | Add cache pruning and dashboard metrics for hit-rate and stale-key churn. | Medium
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Evidence verifier firewall added for LLM candidates | Done | src/llm/evidenceVerifier.js + extractCandidatesLLM integration + tests | Consider strict mode default after all evidence packs include complete snippet primitives. | High
05 | LLM-POWERED FIELD EXTRACTION & DETERMINISTIC PARSING | Candidate merger + conflict resolver module implemented | Done | src/scoring/candidateMerger.js + test/candidateMerger.test.js | Wire merger outcomes into review queue prioritization and UI surfacing. | Medium
06 | IDENTITY GATE & PRODUCT DISAMBIGUATION SYSTEM | Identity gate implemented and strict | Done | src/validator/identityGate.js + test/identityGate.test.js | Ensure publish pipeline blocks promotion when identity ambiguous | High
06 | IDENTITY GATE & PRODUCT DISAMBIGUATION SYSTEM | Final outputs include publishable=false + reason=identity_ambiguous when needed | Done | src/pipeline/runProduct.js + src/exporter/finalExporter.js + test/finalExporter.test.js | Explicit publishable=false and publish_blockers now prevent final promotion; ambiguity remains blocked for review. | High
07 | PIPELINE ORCHESTRATOR, QUEUE MANAGEMENT & 24/7 DAEMON | Multi-round orchestrator exists | Done | src/runner/runUntilComplete.js | Make rounds targetFields driven by field_rules required/availability/difficulty/effort | High
07 | PIPELINE ORCHESTRATOR, QUEUE MANAGEMENT & 24/7 DAEMON | 24/7 daemon exists | Done | src/daemon/daemon.js + test/daemon.test.js | Daemon loop now supports concurrency caps, stale re-crawl scans, per-job failure retry bookkeeping, and graceful signal drain behavior. | Medium
07 | PIPELINE ORCHESTRATOR, QUEUE MANAGEMENT & 24/7 DAEMON | Effort model budgets are contract-driven per-field | Done | src/runner/runUntilComplete.js + test/runUntilComplete.test.js | Contract effort planning now reads required_level/availability/difficulty/effort and scales round budgets for deep fill rounds. | High
07 | PIPELINE ORCHESTRATOR, QUEUE MANAGEMENT & 24/7 DAEMON | Stop conditions (no new URLs/fields, budget exhaustion) | Done | src/runner/runUntilComplete.js + test/runUntilComplete.test.js | Stop logic now includes required-search exhaustion plus existing no-progress/quality/budget checks with explicit stop_reason outputs. | Medium
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Review candidates persisted for every field with provenance | Done | src/review/reviewGridData.js + src/pipeline/runProduct.js + test/reviewGridData.test.js | Review artifacts now emit full per-field candidates with evidence into final/<category>/<product>/review and legacy output paths. | High
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Review queue output produced per product | Done | src/review/reviewGridData.js writeProductReviewArtifacts()/writeCategoryReviewArtifacts() + src/cli/spec.js review queue/build | Queue is generated as _review/<category>/queue.json and sorted by urgency for triage. | High
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Overrides file applied deterministically without recrawl | Done | src/review/overrideWorkflow.js + test/reviewOverrideWorkflow.test.js | Candidate/manual overrides now preserve provenance fields and runtime validation blocks invalid finalize unless draft mode is chosen. | High
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | GUI Review Grid exists for selecting candidates | Done | tools/gui/app.py Review Grid tab + review CLI integration | Added Excel-order review matrix, queue triage controls, candidate drawer, manual override, finalize, and suggestion submission actions. | Medium
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Final publishing outputs written (spec.json/summary/etc) | Done | src/publish/publishingPipeline.js + src/cli/spec.js publish | Publishing now merges latest ProductRecord with approved overrides, re-validates via runtime gate, writes versioned published outputs, and updates category index/changelog. | High
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Continuous monitoring (accuracy, unk rates, evidence failures) | Done | src/publish/publishingPipeline.js runAccuracyBenchmarkReport()/buildAccuracyTrend() + CLI | Continuous accuracy monitoring now writes latest + dated reports, includes per-group metrics, and flags >=5% per-field regressions. | Medium
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Ops readiness: llm-health, queue e2e, caching verification | Done | src/cli/spec.js source-health/llm-metrics/provenance/changelog + tests | Ops command surface now includes provenance lookup, changelog queries, source-health rollups, and LLM billing metrics with budget checks. | Medium
10 | MULTI-CATEGORY EXPANSION, INTEGRATION TESTING & PRODUCTION HARDENING | Multi-category expansion scaffolding | Done | helper_files/monitor/_generated/* + helper_files/keyboard/_generated/* via phase10-bootstrap + compile-rules --all + src/phase10/expansionHardening.js + src/field-rules/compiler.js + test/phase2CompilerPipeline.test.js | Scaffolds now compile from starter workbooks using auto-bootstrap workbook_map fallback; monitor/keyboard generated artifacts and golden manifests are present. | High
10 | MULTI-CATEGORY EXPANSION, INTEGRATION TESTING & PRODUCTION HARDENING | Hardening: fuzz tests, load tests, failure injection | Done | src/phase10/expansionHardening.js runQueueLoadHarness()/runFailureInjectionHarness()/runFuzzSourceHealthHarness() + src/cli/spec.js hardening-harness + tests | Harnesses now cover queue load, retry/failure injection, and malformed-source fuzzing; extend with higher-volume CI stress profiles as throughput scales. | Medium
10 | MULTI-CATEGORY EXPANSION, INTEGRATION TESTING & PRODUCTION HARDENING | Production hardening: dependency cleanup, security, compliance | Done | src/phase10/expansionHardening.js runProductionHardeningReport() + src/cli/spec.js hardening-report + test coverage | Hardening diagnostics now report lockfile/dependency/docs/gitignore hygiene; expand into automated remediation playbooks in ops runbooks. | Medium
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Shared schema pack exists under categories/_shared for generated artifacts | Done | categories/_shared/base_field_schema.json + base_component_schema.json + artifact schemas | Keep schemas versioned and align stricter validation with authoring contract evolution | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Per-field required metadata validation enforced (required_level/availability/difficulty/effort/evidence/unknown_reason) | Done | src/field-rules/compiler.js validateRules() metadata audit + tests | Keep metadata schema strict and fail CI on missing contract metadata | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | init-category generates user-editable _source/field_catalog.xlsx template | Done | src/field-rules/compiler.js initCategory() + ExcelJS starter workbook + tests | Keep workbook format stable and intuitive for non-technical editors | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Compiler normalization enforces required schema blocks per field (contract/priority/parse/evidence) | Done | src/field-rules/compiler.js normalizeFieldRulesForPhase1() + validate-rules pass | Keep normalization defaults stable and schema-aligned across categories | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Regression test covers sparse field normalization (missing evidence object) | Done | test/phase1FieldRulesCompiler.test.js normalizeFieldRulesForPhase1 backfill test | Expand regression set for future control-plane edge cases | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Phase 1 verification pass: compile-rules + validate-rules successful on mouse (75-field scope) | Done | node src/cli/spec.js compile-rules --category mouse --local + validate-rules --category mouse --local | Use this as go/no-go gate before Phase 2 changes | High
01 | CATEGORY SCHEMA & FIELD RULES AUTHORING SYSTEM | Dry-run diff is stable (no-change) when using existing workbook_map/control-plane context | Done | src/field-rules/compiler.js dry-run staging + test/phase1FieldRulesCompiler.test.js | Retain semantic compare rules for volatile keys only. | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | compile-rules --all batch mode for initialized categories | Done | src/field-rules/compiler.js compileRulesAll() + src/cli/spec.js compile-rules --all + test/phase2CompilerPipeline.test.js | Batch compile path supports discovery + dry-run aggregation for category fleets. | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Golden fixture lifecycle commands (create-golden/test-golden/accuracy-report) | Done | src/testing/goldenFiles.js + src/cli/spec.js create-golden/test-golden/accuracy-report + test/goldenFiles.test.js | Supports single-case authoring, Excel-seeded batch creation, fixture validation, and accuracy reporting. | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | Generated manifest.json with SHA-256 artifact verification | Done | src/field-rules/compiler.js ensurePhase1Artifacts() manifest generation + validateRules() manifest verification | Manifest now tracks hashed generated artifacts and validation checks integrity. | High
02 | ARTIFACT COMPILATION PIPELINE & VALIDATION TOOLCHAIN | compile-report and rules-diff operational reporting commands | Done | src/field-rules/compiler.js readCompileReport()/rulesDiff() + src/cli/spec.js compile-report/rules-diff + test/phase2CompilerPipeline.test.js | Provides immediate post-compile diagnostics and breaking-change classification output. | Medium
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Phase 3 TDD baseline added for engine API (core smoke coverage) | Done | test/fieldRulesEngine.test.js (13 focused API tests including strict evidence, cross-validation types, normalization_fn, determinism) | Expand to 50+ normalization cases per type and integration/golden regression coverage. | High
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Normalization helper library extracted for reusable coercion/unit parsing | Done | normalization-functions.js expanded with polling/dimension/color/latency/date/boolean helpers + dedicated unit tests. | Add additional category-specific helper functions as new contracts appear. | Medium
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Runtime gate integrated into runProduct (engine-first normalization with no-bypass rejection path) | Done | src/engine/runtimeGate.js + src/pipeline/runProduct.js runtime_engine summary + failure demotion path | Enable fieldRulesEngineEnforceEvidence once deterministic snippet_id/quote coverage is complete across crawler/extractors. | High
03 | FIELD RULES RUNTIME ENGINE (NO BYPASS) | Runtime gate TDD coverage added (normalization, closed enum rejection, cross-validation, strict evidence mode) | Done | test/runtimeGate.test.js (5 tests) + npm test (198 passing) | Expand to golden replay determinism + confidence calibration metrics in next Phase 3 pass. | High
06 | IDENTITY GATE & PRODUCT DISAMBIGUATION SYSTEM | Per-run identity_report.json artifact emitted with page-level decisions/reason codes | Done | src/validator/identityGate.js buildIdentityReport() + src/pipeline/runProduct.js runBase/identity_report.json | Report now records page confidence/decision/matched hard IDs/tokens and reconciliation status for audit + review grid inputs. | High
06 | IDENTITY GATE & PRODUCT DISAMBIGUATION SYSTEM | Phase 1-6 verification sweep executed (compile/validate/golden verify + runtime dry-run artifacts) | Done | node src/cli/spec.js compile-rules/validate-rules/field-rules-verify + run-one --dry-run + npm test (226 passing) | Confirmed identity_report.json, run evidence artifacts, final evidence/history updates, and publishable=false gating on ambiguous run. | High
07 | PIPELINE ORCHESTRATOR, QUEUE MANAGEMENT & 24/7 DAEMON | Queue CLI supports add/add-batch/list/stats/retry/pause/clear | Done | src/cli/spec.js queue command + test/queueCli.test.js | Queue command surface implemented with local/S3 parity and CSV batch ingestion. | High
07 | PIPELINE ORCHESTRATOR, QUEUE MANAGEMENT & 24/7 DAEMON | Queue retry backoff + stale recrawl marking implemented | Done | src/queue/queueState.js + test/queueState.test.js | Exponential retry scheduling, hard-fail at max attempts, and stale completed-product recrawl marking are now covered by tests. | High
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Suggestion feedback files for enum/component/alias are persisted with evidence | Done | src/review/suggestions.js + src/cli/spec.js review suggest + test/reviewSuggestions.test.js | Pending suggestions are written under helper_files/<category>/_suggestions with dedupe and evidence requirement. | Medium
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Bulk triage actions available in GUI for review workflow | Done | tools/gui/app.py Review Grid tab + src/cli/spec.js review approve-greens + src/review/overrideWorkflow.js | One-click Approve Greens is now wired in GUI and CLI, writing deterministic candidate-selection overrides in bulk. | Medium
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Keyboard-first shortcuts implemented (Tab/1-9/Ctrl+A/Ctrl+S) | Done | tools/gui/app.py Review Grid tab (Quick Action + Candidate # quick-apply form) | Keyboard-first workflow now includes quick actions for ctrl+a/ctrl+s/ctrl+p/ctrl+f plus 1-9 candidate quick apply via Candidate # form with Enter submit. | High
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Live queue update channel (WebSocket) implemented | Done | src/review/queueWebSocket.js + src/cli/spec.js review ws-queue + test/reviewQueueWebSocket.test.js | Native /ws/queue websocket channel now pushes snapshot + queue_updated events with changed product ids; GUI keeps polling fallback for reliability. | Medium
08 | DATA REVIEW GRID GUI & HUMAN-IN-THE-LOOP OVERRIDES | Review throughput metrics exposed (products/hour, overrides/product, avg review time) | Done | src/review/overrideWorkflow.js buildReviewMetrics() + src/cli/spec.js review metrics + tools/gui/app.py Review Grid metrics panel | Metrics now roll up from audited override/finalize metadata and are visible in the review workstation. | Medium
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Publish CLI supports single product and all-approved batches | Done | src/cli/spec.js commandPublish + test/publishCli.test.js | Supports --product-id and --all-approved workflows with incremental publish behavior. | High
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Published artifact set includes current/compact/provenance/changelog/jsonld/markdown | Done | src/publish/publishingPipeline.js writePublishedProductFiles() | Per-product published folder now includes full + compact payloads, provenance export, changelog, JSON-LD, markdown, and version archives. | High
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Bulk export outputs generated (CSV/XLSX/SQLite/feed) | Done | src/publish/publishingPipeline.js writeBulkExports() | Writes all_products.csv, all_products.xlsx, all_products.sqlite (python sqlite fallback), and feed.json. | High
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Provenance and changelog query APIs available via CLI | Done | src/publish/publishingPipeline.js readPublishedProvenance()/readPublishedChangelog() + CLI | Supports field-level provenance trace and full per-product changelog lookup. | Medium
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Accuracy benchmark + trend commands operational | Done | src/publish/publishingPipeline.js runAccuracyBenchmarkReport()/buildAccuracyTrend() + test/publishingPipeline.test.js | Adds accuracy-benchmark and accuracy-trend CLI workflows with persisted report artifacts. | High
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Source health monitoring command operational | Done | src/publish/publishingPipeline.js buildSourceHealth() + CLI | Aggregates attempts/success/block rates from evidence source history files. | Medium
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | LLM performance/cost monitoring command operational | Done | src/publish/publishingPipeline.js buildLlmMetrics() + CLI | Aggregates ledger costs/tokens by model and evaluates period budget thresholds. | Medium
09 | PUBLISHING PIPELINE, OUTPUT FORMATS & CONTINUOUS ACCURACY MONITORING | Drift detection + auto-republish scheduler | Done | src/publish/driftScheduler.js + src/daemon/daemon.js drift hooks + src/cli/spec.js drift-scan/drift-reconcile + test/driftScheduler.test.js | Daily drift hash scan now enqueues drift_reextract jobs; post-rerun reconcile auto-queues manual review on value diffs, quarantines evidence failures, and auto-republishes when no diff remains. | High
11 | ADDENDUM: PRACTICAL CHATMOCK INTEGRATION ON WINDOWS (MODEL TIERING + AUTORECOVERY) | Lifecycle control: start/stop/restart via docker compose -f <path> | Done | src/llm/cortex_lifecycle.js + src/cli/spec.js cortex-start/stop/restart + scripts/chatmock-ctl.bat | Implements Docker Compose remote control without copying ChatMock sources; verified ChatMock docker-compose has restart: unless-stopped. | High
11 | ADDENDUM: PRACTICAL CHATMOCK INTEGRATION ON WINDOWS (MODEL TIERING + AUTORECOVERY) | Readiness check uses /v1/models with robust base URL normalization | Done | src/llm/cortex_lifecycle.js status()/ensureRunning() + stripTrailingV1() + test/cortexLifecycle.test.js | Readiness is based on API model listing instead of process-only checks. | High
11 | ADDENDUM: PRACTICAL CHATMOCK INTEGRATION ON WINDOWS (MODEL TIERING + AUTORECOVERY) | Router defaults to GPT-5 Low and escalates to High only when needed with deep cap | Done | src/llm/cortex_router.js + src/config.js CORTEX_* model/escalation vars + test/cortexRouter.test.js | Deep usage is bounded by CORTEX_MAX_DEEP_FIELDS_PER_PRODUCT. | High
11 | ADDENDUM: PRACTICAL CHATMOCK INTEGRATION ON WINDOWS (MODEL TIERING + AUTORECOVERY) | Circuit breaker + sidecar fallback to non-sidecar execution | Done | src/llm/cortex_health.js + src/llm/cortex_client.js + test/cortexClient.test.js | Sidecar failures/unavailability no longer block progression; fallback path is explicit. | High
11 | ADDENDUM: PRACTICAL CHATMOCK INTEGRATION ON WINDOWS (MODEL TIERING + AUTORECOVERY) | Pipeline/CLI integration and verification coverage for Phase 11 paths | Done | src/pipeline/runProduct.js cortex_sidecar summary integration + src/cli/spec.js cortex-* commands + test/cortexCli.test.js + test/cortexConfig.test.js | Validated with npm test (273 passing) and live cortex-status/ensure/run-pass command checks. | Medium